Aara — Decisions Needed

Twelve open questions blocking finalization of the Aara PRD and start of Phase-0 alpha. Each entry names an owner, a due date, the option-space, and a current recommendation.

| Owner | Raja (Product) |
| --- | --- |
| Audience | Eng lead, IT/Security, AT&T AI team lead, BCLM project leadership |
| Companion to | Aara_Teams_Aggregator_PRD.docx v0.2 (PRD §15 Open Questions) |
| Updated | May 26, 2026 |
| Status | Open — none resolved yet |

1. Summary

Twelve decisions block forward motion. Five sit with the AT&T AI team, three with IT/Network/Apps, three with Product, one with Compliance. Six of them must close before Phase-0 alpha can kick off; the rest before beta. Recommendation for every question is provided below — most are non-controversial and exist mainly to confirm owners and lead times.

Decision groups at a glance

| Track | Owner | Items | Blocks |
| --- | --- | --- | --- |
| AskAT&T integration | AT&T AI team | Q3, Q4, Q5, Q6 (4) | Alpha for 3 of 4; beta for 1 |
| IT / Network / Apps | IT / Network / App Catalog | Q2, Q7, Q11 (3) | Alpha |
| Product | Raja (Product) | Q1, Q8, Q10, Q12 (4) | Alpha for 3; beta for 1 |
| Compliance | Compliance / Records | Q9 (1) | Alpha |

2. Decisions tracker

One row per decision. Detailed context and option-space follow in §3–§6.

| ID | Question | Owner | Due | Recommendation | Status |
| --- | --- | --- | --- | --- | --- |
| Q1 | Which channels/group chats are in initial Aara scope? | Raja (PM) | Jun 2 | BCLM-eng, BCLM-leads, BCLM-vendor, BCLM-status — confirm with project lead. | Open |
| Q2 | IT owner for Teams app registration & RSC approval? | IT — Identity | Jun 2 | Identify named contact; aim for app registered and consented by Jun 9. | Open |
| Q3 | AskAT&T: which exact model + version do we pin for v1? | AT&T AI team | Jun 5 | Pin the latest GPT-4-class model AskAT&T offers; document deprecation calendar. | Open |
| Q4 | AskAT&T: rate limits, concurrency, reserved capacity for <30s SLO? | AT&T AI team | Jun 5 | Reserve 12 RPS sustained / 30 RPS burst; revisit at beta. | Open |
| Q5 | AskAT&T: is structured/JSON-mode output native, or do we wrap with retry? | AT&T AI team | Jun 5 | Native preferred; wrap with schema-validation retry as fallback. | Open |
| Q6 | AskAT&T: does the platform expose an embeddings endpoint? | AT&T AI team | Jul 7 | If yes, use for AI Search vector index; if no, drop semantic search from v1. | Open |
| Q7 | Network path to AskAT&T: ExpressRoute / Private Link / VNet peering? | IT — Network | Jun 5 | ExpressRoute via existing AT&T circuit; confirm capacity & 2-week lead time. | Open |
| Q8 | Planner write-back: bidirectional in v1, or one-way in v1.1? | Raja (Product) | Jul 7 | One-way (bot → Planner) in v1.1; revisit bi-di for v2. | Open |
| Q9 | Retention policy on raw messages vs. extracted items? | Compliance / Records | Jun 2 | Raw: 90 days. Extracted (action items, decisions, follow-ups, digests): indefinite while project active. Audit log: 18 months. | Open |
| Q10 | Authorization model for /Aara channels add? | Raja (Product) | Jun 2 | Named Aara admin role only; admin assigned by project lead. | Open |
| Q11 | Teams app catalog approval — lead time and gate? | IT — App Catalog | Jun 2 | Submit to catalog by Jun 9; assume 5-business-day SLA; raise to IT if longer. | Open |
| Q12 | Does the bot need to handle non-English content in v1? | Raja (Product) | Jun 2 | English-only v1; revisit when a non-English use case appears in beta. | Open |

3. AskAT&T integration (5 decisions, owner: AT&T AI team)

These four questions sit on the critical path because the chosen AskAT&T model, capacity, and API surface shape every layer of the Azure bot. Schedule the AT&T AI team conversation in the first week.

Q3 · Which exact AskAT&T model + version do we pin for v1?

Owner: AT&T AI team    Due: Jun 5    Blocks: Phase-0 alpha (Jun 9)

Context. AskAT&T exposes a catalog of approved models. The bot needs a single pinned model + version per release so behavior is reproducible. We also need a deprecation calendar so we can plan migration if the model is retired during the Aara project window.

Options.

Pin a GPT-4-class model AskAT&T currently supports (recommended).

Pin a smaller/cheaper model (faster, weaker structured-output behavior — likely fails alpha exit criterion).

Pin a versioned alias rather than a model snapshot (less reproducible).

Recommendation. Pin the latest GPT-4-class snapshot AskAT&T offers. Track AT&T-AI's deprecation calendar in this memo and revisit at each release. Validate structured-output behavior in alpha.

Q4 · AskAT&T rate limits, concurrency, reserved capacity?

Owner: AT&T AI team    Due: Jun 5    Blocks: Phase-0 alpha (Jun 9)

Context. PRD §6.3 sets a < 30s response-time target for on-demand summaries on windows up to 7 days. That translates to LLM concurrency under load. We need explicit quota numbers, and likely a reserved-capacity arrangement so we are not throttled at peak.

Options.

Use shared AskAT&T capacity (cheaper but throttle-risk; likely fails SLO).

Reserve 12 RPS sustained / 30 RPS burst for Aara (recommended at v1 scale).

Defer the SLO until measured load is known (delays beta exit criteria).

Recommendation. Negotiate 12 RPS sustained / 30 RPS burst reserved capacity for v1, with a re-evaluation at beta. Document the SLA in a follow-up addendum to this memo.

Q5 · Is structured / JSON-mode output native, or do we wrap with retry?

Owner: AT&T AI team    Due: Jun 5    Blocks: Phase-0 alpha (Jun 9)

Context. Action-item / decision extraction depends on reliable JSON output. Native JSON mode (where the model is constrained to valid JSON by the inference runtime) is materially more reliable than prompt-only JSON. PRD §6.2 mandates source-message citations on every item — these are easier to enforce with a strict schema.

Options.

AskAT&T offers native JSON mode → use directly (recommended).

AskAT&T does not → wrap our client with a schema-validation retry loop (3 attempts, then triage).

Mixed: native mode available for some models, not others → pin a model that supports it.

Recommendation. Prefer native JSON mode. If unavailable on the pinned model, implement a 3-retry schema-validation wrapper in the bot backend and budget the extra latency in §6.3 SLO planning.

Q6 · Does AskAT&T expose an embeddings endpoint?

Owner: AT&T AI team    Due: Jul 7    Blocks: Phase-1 beta (Jul 7) — does NOT block alpha

Context. PRD §8.2 mentions Azure AI Search as an optional v1 component for semantic recall across Aara history. Vector indexing requires an embeddings model. If AskAT&T does not expose one, we either drop semantic search from v1 or escalate for a separate approved embeddings path.

Options.

AskAT&T exposes an embeddings endpoint → use directly, index in AI Search (recommended if available).

Not available → drop semantic search from v1 scope, revisit in v2.

Use a different AT&T-approved embeddings service → adds another integration; only if obviously available.

Recommendation. If embeddings are available, build the AI Search index in alpha. If not, drop semantic search and remove the AI Search line-item from the deployment view.

4. IT / Network / Apps (3 decisions, owner: IT)

Standard enterprise plumbing — none of these decisions are technically hard, but each carries 1–3 weeks of lead time. Start the IT conversation in the first week.

Q2 · Who in IT owns Teams app registration + RSC approval?

Owner: IT — Identity    Due: Jun 2    Blocks: Phase-0 alpha (Jun 9)

Context. Aara installs as a Teams app and requests Resource-Specific Consent (RSC) scopes per team. App registration in Entra ID and RSC permission consent are both gated by IT. We need a named owner and lead time.

Options.

Single named contact in IT-Identity (recommended).

Generic ServiceNow queue (slower, less accountable).

Self-service via internal devportal if available (fastest but rarely an option for new apps).

Recommendation. Get a named Identity-team contact. Aim for app registered + RSC consent ready by Jun 9.

Q7 · Network path to AskAT&T: ExpressRoute / Private Link / VNet peering?

Owner: IT — Network    Due: Jun 5    Blocks: Phase-0 alpha (Jun 9)

Context. PRD §8.4 commits to a private-network path to AskAT&T (no public-Internet hop). The architecture diagrams assume ExpressRoute, but the actual choice depends on how AskAT&T is exposed and what the AT&T-Azure network team already has provisioned.

Options.

Reuse an existing ExpressRoute circuit AT&T already has into Azure (recommended — fastest).

New Private Link service (more isolated but new infra; longer lead time).

VNet peering to an AT&T-managed Azure VNet that fronts AskAT&T (good if available).

Recommendation. Reuse existing ExpressRoute. Confirm BGP path to AskAT&T endpoint and capacity. Plan 2-week lead time on any new routes.

Q11 · Teams app catalog approval — lead time and gate?

Owner: IT — App Catalog    Due: Jun 2    Blocks: Phase-1 beta (Jul 7) — does NOT block alpha

Context. Production Aara needs to be published into the AT&T tenant Teams app catalog before broad rollout. App-catalog approvals usually carry an SLA and a review process (typically 5 business days but can be longer).

Options.

Standard catalog approval workflow (recommended; submit early).

Side-loaded admin install only (works for alpha but blocks beta).

Pre-approve via Teams admin policy override (faster but requires sign-off).

Recommendation. Submit to catalog by Jun 9 so beta is unblocked. If the standard SLA is >5 business days, escalate to IT leadership.

5. Product (4 decisions, owner: Raja)

These are decisions I can close myself with the project-lead conversation. None are technically hard.

Q1 · Which channels and group chats are in initial Aara scope?

Owner: Raja (Product)    Due: Jun 2    Blocks: Phase-0 alpha (Jun 9)

Context. PRD §5 Mode A requires a designated channel list. We do not have one yet from the project lead. The list anchors alpha scope — too narrow and we miss signal, too broad and we capture banter.

Options.

Start with 2 channels for alpha (BCLM-eng + BCLM-leads), expand at beta (recommended).

Add all 5 known BCLM-prefixed channels day one (more signal, more noise risk).

Defer the decision and let the admin add channels at install time (works but no calibration).

Recommendation. Two channels for alpha: BCLM-eng and BCLM-leads. Expand to BCLM-vendor, BCLM-status, and BCLM-design at beta after the recall metric is measured.

Q8 · Planner write-back: bidirectional in v1, or one-way in v1.1?

Owner: Raja (Product)    Due: Jul 7    Blocks: Phase-1.1 (Aug)

Context. PRD §9 lists Microsoft Planner write-back as a v1.1 capability. The question is whether we sync only bot → Planner (one-way) or also let Planner status changes reflect back into the Aara digest (bidirectional).

Options.

One-way (bot → Planner) in v1.1 (recommended — simpler, lower risk).

Bidirectional in v1.1 (more useful for power users but adds reconciliation complexity).

Defer all Planner integration to v2 (loses a clear v1.1 win).

Recommendation. One-way write-back in v1.1. Reconsider bidirectional for v2 once Planner usage data is measured.

Q10 · Authorization model for /Aara channels add?

Owner: Raja (Product)    Due: Jun 2    Blocks: Phase-0 alpha (Jun 9)

Context. PRD §6.5 grants channel-management to the Aara admin role. The open question is whether anyone in a designated channel can run /Aara channels add, or only a named admin.

Options.

Anyone in the channel (more flexible, more risk of accidental scope creep).

Named Aara admin role only (recommended — fewer accidents, clear accountability).

Team owner-only (works but admin and team-owner are often different people).

Recommendation. Named Aara admin role only. Admin is assigned by the BCLM project lead at install time. Anyone can run read-only commands like /Aara summary.

Q12 · Non-English language content in v1?

Owner: Raja (Product)    Due: Jun 2    Blocks: Phase-0 alpha (Jun 9)

Context. Aara messages in the AT&T tenant are predominantly English, but some cross-functional chats include other languages. The pinned AskAT&T model presumably supports multilingual extraction; the question is whether we test for it.

Options.

English-only v1, revisit at beta if non-English content shows up (recommended — keeps alpha scope small).

Multilingual v1 (more testing surface, no clear demand signal yet).

Recommendation. English-only v1. Add multilingual scope to the v2 backlog if beta surfaces a real use case.

6. Compliance (1 decision, owner: Compliance / Records)

Q9 · Retention policy on raw messages vs. extracted items?

Owner: Compliance / Records    Due: Jun 2    Blocks: Phase-0 alpha (Jun 9)

Context. PRD §10 proposes 90-day raw message retention and indefinite extracted-item retention (until the project is archived). Compliance needs to confirm both numbers fit AT&T records-management policy and any applicable regulations.

Options.

90-day raw / indefinite extracted (PRD default — recommended).

30-day raw / 12-month extracted (more conservative; loses long-tail recall).

No raw retention at all — extract-then-discard (lowest privacy risk; impossible to re-extract if the LLM is bad).

Recommendation. Confirm PRD defaults. If Compliance pushes for shorter, propose 30-day raw / 24-month extracted as a fallback.

7. Cadence

Weekly review every Monday until all 12 are closed. Owner: Raja. Time-boxed to 15 min.

Each decision moves to status Pending Review once an option is recommended by the owner, Closed once accepted by leadership.

This memo is the single source of truth — do not let decisions live in chat. Status is mirrored in the PRD §15 at each PRD version bump.

If a decision misses its due date, the owner notes the slip and a new date on this memo, with the downstream impact called out.